## Sheet1
name | effort | start | end | developer | user story | status
Allow user to add iteration name and duration. | 1 | 01/04/2021 | 07/04/2021 | Reem | As a scrum master, so that I define the iteration, I want to add its specific details. | Completed
Allow user to add iteration start date. | 3 | 01/04/2021 | 07/04/2021 | Shadi | As a scrum master, so that I define the iteration, I want to add its specific details. | Completed
Allow user to add user stories and tasks. | 5 | 01/04/2021 |  | George | As a scrum master, so that I define the iteration, I want to add its specific details. | In Progress
Save iteration to database. | 2 | 01/04/2021 |  | Wafic | As a scrum master, so that I define the iteration, I want to add its specific details. | Open
Allow user to add user story name and size. | 2 | 01/04/2021 | 04/04/2021 | Reem | As a scrum master, so that I can define a backlog, I want to create new user stories. | Completed
Save user story to database. | 2 | 01/04/2021 | 05/04/2021 | George | As a scrum master, so that I can define a backlog, I want to create new user stories. | Completed
Allow user to add task name, effort, start, developer. | 5 | 01/04/2021 | 05/04/2021 | Shadi | As a scrum master, so that I complete the details of a user story, I want to add tasks for each user story. | Completed
Set task status to Open by default. | 2 | 01/04/2021 | 06/04/2021 | Wafic | As a scrum master, so that I complete the details of a user story, I want to add tasks for each user story. | Completed
Save task to database. | 2 | 01/04/2021 | 07/04/2021 | Wafic | As a scrum master, so that I complete the details of a user story, I want to add tasks for each user story. | Completed
Allow developer to change status of assigned task. | 4 | 01/04/2021 |  | Reem | As a developer, so that I can update my progress, I want to change the status of the task assigned to me. | Open
Set end date to the date that status is changed to completed. | 2 | 01/04/2021 |  | George | As a developer, so that I can update my progress, I want to change the status of the task assigned to me. | Open
Save status to database. | 2 | 01/04/2021 |  | George | As a developer, so that I can update my progress, I want to change the status of the task assigned to me. | Open
Show user story status of the iteration. | 4 | 01/04/2021 |  | Shadi | As a project member, so that I can view the current iteration, I want to be able to genrate a report. | Open
Plot Burn-down chart. | 5 | 01/04/2021 |  | Shadi | As a project member, so that I can view the current iteration, I want to be able to genrate a report. | Open
Create Iteration database. | 5 | 01/04/2021 |  | Reem | As a manager, so that I can view an iteration, I want to create a database for the system. | In Progress
Create task database. | 7 | 01/04/2021 |  | Wafic | As a manager, so that I can view an iteration, I want to create a database for the system. | In Progress