## Sheet1
name | effort | start | end | developer | user story | status
T1 name | 2 | 02/12/2021 |  | developer name | US name 1 | Open
T2 name | 3 | 02/12/2021 |  | developer name | US name 1 | Open
T3 name | 3 | 02/12/2021 |  | developer name | US name 1 | Open
T1 name | 3 | 02/12/2021 |  | developer name | US name 2 | Open
T2 name | 1 | 02/12/2021 |  | developer name | US name 2 | Open
T1 name | 2 | 02/12/2021 |  | developer name | US name 3 | Open
T2 name | 4 | 02/12/2021 |  | developer name | US name 3 | Open
T3 name | 4 | 02/12/2021 |  | developer name | US name 3 | Open
T4 name | 4 | 02/12/2021 |  | developer name | US name 3 | In Progress
T5 name | 2 | 02/12/2021 | 03/12/2021 | developer name | US name 3 | Completed
T6 name | 3 | 02/12/2021 | 04/12/2021 | developer name | US name 3 | Completed
T1 name | 3 | 02/12/2021 | 04/12/2021 | developer name | US name 4 | Completed
T2 name | 3 | 02/12/2021 | 05/12/2021 | developer name | US name 4 | Completed
T3 name | 3 | 02/12/2021 | 05/12/2021 | developer name | US name 4 | Completed
New Task 1 | 5 | 11/11/2020 | 13/04/2021 | Reem | New US story | Completed
T11 | 2 | 01/04/2021 | 03/04/2021 | Reem | US1 | Completed
T12 | 3 | 01/04/2021 | 01/04/2021 | Shadi | US1 | Completed
T21 | 5 | 05/04/2021 | 10/04/2021 | Wafic | US2 | Completed
T22 | 3 | 06/04/2021 |  | Shadi | US2 | Open
T31 | 6 | 03/04/2021 | 04/04/2021 | Shadi | US3 | Completed
T32 | 9 | 02/04/2021 |  | Wafic | US3 | Open
T41 | 8 | 14/04/2021 |  | Shadi | US4 | Open
T42 | 2 | 03/04/2021 | 04/04/2021 | Shadi | US4 | Completed